## Start Here
CS 4632 - Modeling and Simulation - Course Project - Project Proposal |  | Name: Ashton Miller |  | NetId: amill287
Project Proposal - Documentation and research
|  | Class: | CS 4632 - Modeling and Sim | Your Notes:
|  | Section: | WO1
Overview | Important Note: This project proposal will help you start organizing your thoughts and plans. I do not expect everything to be fully mapped out or perfectly planned at this stage. Please provide as much detail as you can, but understand that the process of filling in these boxes is here to help you think through your project. The proposal is a living document (for continuous usage even after submission); it’s okay if some sections are initially incomplete or need revisions as your project evolves. Use this as a guide to keep your work organized and to ensure that you cover your project's critical aspects. Where you see bolded letters on the "Start Here" sheet, filling those in can help you get started. Bolded sections in the other pages/sheets within this document, are there to guild you through the process of filling in your proposal. | Year and Semester (fall/spring) | Fall
Purpose | The purpose of this project is to study, implement, test, and evaluate a specific model using principles learned in the course, leading to a comprehensive understanding of the model's behavior and applications. For the proposal, define your project’s end-to-end goal, select and describe the model you plan to study, outline how you will implement and test the model, and detail your initial simulation setup, including tools and procedures. This proposal should serve as a foundational plan to guide your project. You can submit your work using this Excel sheet or a traditional PDF/Word Document, with the Excel sheet encouraged to help you stay organized throughout the process. | NOTE: Besure to expand rows and columns, issues can happen with how infomration is displayed | Usage Notes: If you want to insert a line break or new paragraph (such as when you would hit enter, while in type mode use atl+enter. | Enter type mode using F2. | Use Wrap Text to keep text within a box.
Task | Indicate your end-to-end goal for the project. Choose a model to study, implement, test, and evaluate. Develop a general idea of the simulation structure, including experiment setup, implementation methods, tools, and testing procedures. Submit your proposal in the form of an Excel document or a traditional PDF/Word Doc, with the Excel sheet encouraged as a running document to help you stay organized. | YOU ARE FREE TO MAKE ADJUSTMENTS ARE YOU NEED TO, BE SURE TO KEEP YOUR DOCUMENT READABLE IF YOU ADJUST ANYTHING.
Criteria | A successful project will include a clear end-to-end goal, a well-chosen model, a thoughtfully designed simulation structure, and proper documentation of the entire process. The details in the initial proposal do not need to be exhaustive but should provide a solid foundation that will be expanded upon as the project progresses. | Additional Instructions: | End-to-End Goal: Clearly define what you aim to accomplish by the end of the project. This should include a description of the model you plan to study and the expected outcomes of your simulation.
Objectives | Identify and choose a model for study. Develop a preliminary plan for implementation and testing. Organize the project using the Excel sheet or another method. Submit a clear and concise proposal. |  | Model Selection: Specify which model you have chosen and why it is relevant to your project.
Abstract | This project explores the [Golf course pace of play model] by implementing and testing it in a simulated environment, focusing on [the rate at which golf carts are registered as being on the course and their drivers having started their round]. The project will be documented and evaluated based on the model's performance and insights gained. |  | Simulation Structure: Provide a general outline of how you intend to set up your simulation, including the tools you plan to use, the form of implementation, and your testing procedures. This can be refined as you progress in your project.
Hypothesis/Research Questions | How accurately does the [pace of play model] simulate [the situation of paused play from extreme backup]? What are the strengths and limitations of this model in predicting [which holes on the course will be the most backed up]? |  | Documentation Submission: You may submit your proposal using the Excel sheet provided or a traditional PDF document. The Excel sheet is encouraged as it will help you stay organized throughout the project.

## Model Selection
Section | Description | Student Input | Notes/References | Core Outline Features:
Note for Model Selection Sheet
Abstract | Provide a brief summary of the project and the model selected, including the main objectives. | A project that revolves around the pace of play on a golf course that utilizes an imperitive and object oriented approach and usees a queuing system to control the deployment and pace of each group that goes off to play on the golf course. The project aims to not replicate the nature of humans, but to emulate how humans can become imperfectly disordered if not given proper guidance in high traffic situations like this. | [Notes or References]
Model Description | Describe the chosen model, including what it represents, its key components, and how it is typically used. | The model that I have chosen for the project is solely utilized to represent the scenario of an assembly line like procedure in which a golf cart is taken from the cart barn by a golfer and utilized on the course for their round. Key components for this model would include the golf cart as the moving part, the course holes as the tracking area, and the cart barn as the area of origin and finish. This model is used primarily in the golf world on gps tracking systems that keep up with the player on the course and let them know that they are playing too slow. These systems ensure that the courses pace of play is quick and that the overall experience for everyone playing is better. | [Notes or References] | Abstract: | A brief summary of the overall project and how the chosen model fits into the broader scope of your research and simulation goals. | Note: | This section is designed to help you articulate and refine your choice of model for the project. While I encourage you to be as detailed as possible, I understand that some aspects might not be fully clear at this point.
Purpose of Selection | Explain why this model was selected for the project. Include its relevance to your research questions or hypothesis. | This model was selected for the project because the model exhibits the nature of a queuing system where a moving part starts on a metaphorical track(being the golf course) and has to keep pace with other moving parts, wherein if the parts are not properly moving, the flow of the system begins to diminish. | [Notes or References] | Model Description: | Detailed description of the model, including its purpose, components, and how it is typically applied. |  | Use the provided fields to document your thinking and plans, knowing that this document can and should evolve as you progress with your project.
Methodology/Approach | Detail how you plan to implement and use this model in your simulation. Include any specific tools or frameworks you will use. | I plan to take an imperative programming and object oriented approach. The plan for the model that I have is to utilize the python programming language and the SimPy framework to simulate the functions of a queue in the golf course system that I am proposing. To implement the model, I plan to use a queue data structure that queues golf carts by their ID numbers randomly and starts them out at the same location one after the other. This model is only considering the busiest of days of the year where nothing but groups of 4 go out and how the course handles that. Every cart will start at hole 1 and end at 18. Each hole, depending on whether it is a par 3, 4, or 5 will take their own special times due to their physical length. For example a par 3 will on average take about 6 minutes, a par 4 would take about 9 minutes and a par 5 would take about 12 minutes. Each group will have a randomized number of minutes per hole and those numbers will be averaged out with the standard number of minutes previously mentioned to come out to the amount of time they took on that individual hole. As a group slows down, the systems goal is to reach that group and speed them up. In practice the number of minutes that it takes the group will be reduced by the operation of subtraction. This will simulate the process of speeding up pace of play. | [Notes or References] | Purpose of Selection: | Justification for choosing this model, emphasizing its relevance to the project’s objectives. |  | The goal is to create a foundation that you can build on as you move forward.
Assumptions & Limitations | List any assumptions the model makes and its limitations. Explain how these might impact your simulation and analysis. | This model assumes that the amount of time taken per hole will vary dynamically across the golf course. This could impact the simulation by slowing down the pace of play therfore calling for practice of the model as intended. | [Notes or References] | Methodology/Approach: | Explanation of the approach for implementing and testing the model in your simulation. This includes the tools, programming languages, or frameworks you will use.
Expected Outcomes | Describe what you expect to learn or demonstrate by using this model in your simulation. What results do you anticipate? | I expect to learn how a queuing system model can work with a simulation and hope to further understand how the pace of play model works in the real world of golf as well. Im not expecting my model to exactly replicate the nature of humans in real world situations, but moreso how these systems could be improved upon to further the reach of the game and make it a better experience for everyone. | [Notes or References] | Assumptions & Limitations: | Outline any assumptions made by the model and its inherent limitations. Discuss how these factors could affect your simulation and findings.
Hypothesis/Research Questions | Restate your hypothesis or the research questions you aim to explore using this model. | How does the queuing system that is used at every golf course by sending them out group by group in to a central location affec the pace at which the groups are able to play and finish the round? How does this affect the time at which the last golf cart is returned to the cart barn? | [Notes or References] | Expected Outcomes: | A description of what you anticipate learning or proving through the use of this model in your simulations.
Comparison to Other Models | If applicable, compare your chosen model to other potential models. Explain why this one is the best fit for your project. | My project is similar to that of the traffic project where cars on a roadway are backed up from a wreck or some kind of road maintenance. The queuing model I've chosen is best fit for my project because it enforces a sense of order to an otherwise unorderly system. | [Notes or References] | Hypothesis/Research Questions: | Reiteration of the key hypothesis or research questions that your simulation using this model aims to address.
Implementation Feasibility | Assess the feasibility of implementing this model. Consider factors like the complexity of the model, available resources, and potential challenges. | I believe that the model is very feasible to implement so long as the adequate process of keeping up with the milestones is followed correctly and the development process utilized to its fullest extent. The model itself has elements of complexity but it also has elements of accessibility that make it more understandable to someone with an outsider perspective. The main challenged behind this will be the process of making the queue work and correct the pace like I have proposed. | [Notes or References] | Comparison to Other Models: | (Optional) Compare your chosen model with other potential models to illustrate why this one is the best choice for your project.
References | List any academic papers, articles, or other resources that support your choice of model and its application. | So far I have a baseline knowledge of the imperitive and object oriented approach, so for now I am only using a geeksforgeeks article about the different paradigms that I have found. The link to this article is: https://www.geeksforgeeks.org/introduction-of-programming-paradigms/ | [Notes or References] | Implementation Feasibility: | Evaluate the feasibility of implementing this model, considering resources, complexity, and potential challenges.
|  |  |  | References: | A section to list any relevant literature or resources that support the model selection and its application in your project.

## Implementation Plan
Section | Description | Input | Notes/References
Implementation Overview | Provide a high-level overview of how you plan to implement the model. | The implementation will use a queue structure to simulate and model the pace. |  | Implementation Overview: | A high-level description of how the model will be translated into a working simulation. This might include the general approach you plan to take and any preliminary ideas about structure or algorithms.
Tools & Frameworks | List the tools, programming languages, and frameworks you will use for implementation. | Python language, simpy, and the pycharm ide that will be my primary development environment. |  | Tools & Frameworks: | A list of the specific tools, languages, libraries, or frameworks you plan to use. This could include things like Python, TensorFlow, SimPy, C++, MATLAB, etc.
Key Implementation Steps | Outline the main steps you will take to implement the model, including coding, testing, and any iterations needed. | I plan to program the queue strucure first, incuding the systems times for each individual group by milestone 4, then plan torun and simulate the model by the end of 7 and 8 . |  | Tools & Frameworks: | A list of the specific tools, languages, libraries, or frameworks you plan to use. This could include things like Python, TensorFlow, SimPy, C++, MATLAB, etc.
Resources Needed | Identify any specific resources you will need, such as datasets, libraries, or external APIs. | So far, I will need the math library and random module in python. |  | Resources Needed: | Identification of any specific resources required, such as datasets, external libraries, hardware, or software licenses.
Challenges & Solutions | Anticipate potential challenges in the implementation process and propose possible solutions. | There may be some conceptual issues that I run into when implementing but I plan to do my research that is needed and also reach out to tutors for help and do my due dilligence if needed. |  | Challenges & Solutions: | Anticipation of potential roadblocks and how you plan to address them. This could include technical difficulties, resource limitations, or conceptual challenges.
Preliminary Testing Plan | Describe your initial plan for testing the model after implementation. What tests will you run to ensure it works? | I plan to do a rigorous testing method where I do several runs and compare them to learn how to improve my code if need be. |  | Preliminary Testing Plan: | An outline of how you will initially test the model once it’s implemented. This might involve unit tests, integration tests, or specific scenarios you want to run.
Collaboration & Tools | If working in a team, explain how you plan to collaborate, including tools for version control and communication. | N/A |  | Collaboration & Tools: | If the project involves collaboration, describe how you plan to work together, including the use of version control (e.g., Git), project management tools (e.g., Trello, Asana), and communication platforms (e.g., Slack, Microsoft Teams).
Timeline for Implementation | Provide an estimated timeline for completing the implementation, including any milestones. | I plan to follow along with the syllabus milestones which are as follows: Milestone 2 - Literature Review and Model Documentation Milestone 3 - UML Diagram and Initial Design Milestone 4 - Model Implementation Milestone 5 - Simulation Runs and Data Collection Milestone 6 - Sensitivity Analysis and Scenario Analysis Milestone 7 - Performance Metrics and Optimization Milestone 8 - Validation and Verification |  | Timeline for Implementation: | A breakdown of the timeline, including deadlines for key milestones in the implementation process. This can be an estimated timeline to help guide your work.

## Simulation Details
Simulation Details
Section | Description | Student Input | Notes/References | Detailed Sections:
Simulation Scenarios | Describe the different scenarios you will simulate. What are the key conditions or variations you want to test? | The main scenario that I will be simulating is the scenario of the slow pace of one group slowing down the pace of another group, thus causing backup. |  | Simulation Scenarios: | Describe the different scenarios you plan to simulate. This could involve varying certain conditions, testing under different environments, or exploring multiple use cases.
Variables & Parameters | List the key variables and parameters that will be involved in your simulations. How will you control or measure them? | The main variables I am aim to have in my simulation is the group variable that tracks each group that goes off on the course, the marshall varible that removes time from each group time, simulating a speed up in play, and a return variable that essentially returns true when a groups carts have been returned. |  | Variables & Parameters: | Identify the key variables and parameters that will play a role in your simulations. Explain how you will control these variables and what you will measure.
Data Collection Methods | Explain how you will collect data from your simulations. What metrics or outputs will you be recording? | As of now, the main metric that I will be keeping track of is time spent on the course and focusing on minimizing that as much as possible |  | Data Collection Methods: | Outline how you plan to collect data during your simulations. This could involve logging certain outputs, capturing performance metrics, or recording specific events.
Expected Outcomes | Describe the expected outcomes of your simulations. What results do you anticipate? | I anticipate that the results will initially be sporadically dispersed but after corrections by the marshall, I expect the times of the rounds to go down signigficantly. |  | Expected Outcomes: | Describe the results you expect from your simulations. What hypotheses are you testing, and what do you anticipate the data will show?
Analysis Plan | Outline how you will analyze the data collected from your simulations. What techniques or tools will you use? | The main analysis plan I aim to take is to do a large scale comparison of times from several different days in the conditions that the courses tee times are fully booked. I plan to keep a journal of this in running through each "day" to keep track of how the behavior changes throughout. |  | Analysis Plan: | Explain how you will analyze the data collected from your simulations. This might involve statistical analysis, comparing results across scenarios, or testing specific hypotheses.
Visualization of Results | Describe how you will present the results of your simulations. Will you use charts, graphs, tables, etc.? | I will most likely use a flowchart with each module of the flow chart representing a different hole on the course and include a number for each group that goes out through the day. Once that group is done, their round time will be recorded in a list of times and that list will be used for a bar graph visualizing the results. |  | Visualization of Results: | Plan how you will present your findings. Consider what types of visualizations (e.g., charts, graphs, tables) will best communicate your results.
Simulation Tools | List the software or tools you will use to run your simulations. | The tools that I plan to use are the python programming language and the simpy framework. |  | Simulation Tools: | List the software or tools you will use to run your simulations, such as simulation platforms, programming languages, or custom scripts.
Challenges & Solutions | Anticipate any challenges you might face when running your simulations and propose solutions. | There may be unexpectedly high or low times for a round of golf, so the plan there is to implement a catch all for outliers so that the ouliers are not counted toward the average time per round and the data has a level of uniformity to it. |  | Challenges & Solutions: | Anticipate potential challenges in running your simulations, such as computational limits, data management issues, or unexpected results. Propose strategies to address these challenges.